	DST-BD-FRM-04 (Version 02.0)                              Proposal Schedule                                            10/01/08                                                                                                                            
	Page 1 of 1



[image: image1.png]



Proposal Schedule

RFP: _TOPR # CJB-09-12424_ Title: __ Senior Administrative Support for Defense Centers of Excellence (DCoE) for Psychological Health/Traumatic Brain Injury (PH/TBI) _

	January 2009

	Thurs
	Fri
	Sat
	Sun
	Mon
	Tues
	Wed

	1
	2
	3
	4
	5
	6
	7

	
	
	
	
	Recruiting 4 Sr. Admin Staff
	RFP Review
	Current Staff

Resumes Complete

	
	
	
	
	
	
	

	8
	9
	10
	11
	12
	13
	14

	Kickoff Meeting

10:00AM
	Solution Approach Meeting TBD
	
	
	Questions Due

2:00PM
	Green Team Pricing Review
	Writing

	Entire Team
	Past Performances Due
	
	
	Daily 9:00AM Standup
	Daily 9:00AM Standup
	Daily 9:00AM Standup

	15
	16
	17
	18
	19
	20
	21

	Pink Team Review
	Resumes and Letters of Commitment  Due
	
	
	Writing
	Writing
	Pricing Due

	Daily 9:00AM Standup
	Daily 9:00AM Standup
	
	
	Daily 9:00AM Standup
	Daily 9:00AM Standup
	Daily 9:00AM Standup

	22
	23
	24
	25
	26
	27
	28

	Red Team Review
	Red Recovery
	Reserve Weekend
	Reserve Weekend
	Red Recovery
	Gold Team Review
	Final Production

	Daily 9:00AM Standup
	Daily 9:00AM Standup
	
	
	Daily 9:00AM Standup
	Daily 9:00AM Standup
	Daily 9:00AM Standup

	29
	30
	31
	
	
	
	

	Proposal

Due

2:00PM
	
	
	
	
	
	

	
	
	
	
	
	
	
































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































































	DST-BD-FRM-04 (Version 02.0)                              Proposal Schedule                                            10/01/08                                                                                                                            
	Page 1 of 1



